## Actions
id | created | meeting | team | project | owner | task | due | priority | status | blocked_by | evidence | source | updated | notes | origin | type | next_step | prerequisites | unblocker | effort | basis | closed
2026-09-11-intelligent-tracker-01 | 2026-09-11 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Ashwini | Sign off on the reviewed database design after today's walkthrough. | 2026-09-11 | P1 | open |  | I will be signing off on the Debi after the review | 2026-09-11-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-11-intelligent-tracker-04 | 2026-09-11 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Laxmikant | Work with Ashwini on the overall workflow solution design document. | 2026-09-11 | P1 | open |  | Lakshmi and I will be working on the proper workflow solution design | 2026-09-11-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-11-intelligent-tracker-05 | 2026-09-11 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Johan | Change the CR Notes field UI from a single-line text box to a multi-line text box as Sreekumar requested. | 2026-09-11 | P1 | open |  | Change the UI. I'll change it. | 2026-09-11-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-11-intelligent-tracker-06 | 2026-09-11 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Johan | Write detailed user stories for the Change Request module workflow and share them with Ashwini and Laxmikant. | 2026-09-11 | P1 | open |  | you share it to Ashwini B and Lakshmi Lakshmi | 2026-09-11-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-11-intelligent-tracker-07 | 2026-09-11 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Samuel | Write detailed user stories for the Issues module workflow and present them to Ayush. | 2026-09-11 | P1 | open |  | user stories you figure out and you show me | 2026-09-11-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-15-intelligent-tracker-01 | 2026-09-15 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Laxmikant | Complete the SharePoint list configuration for the DB changes made last Friday and update the UI design to match. | 2026-09-15 | P1 | in_progress |  | Lakshmi will be doing the SharePoint configuration, whatever related to DB changes last Friday we did. | 2026-09-15-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-15-intelligent-tracker-02 | 2026-09-15 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Samuel | Update the Issues module UI design and start Canvas development once it is complete. | 2026-09-16 | P1 | open |  | Samuel also, he will update the UI design. So if it is done, so he will start with the development. | 2026-09-15-activity-tracker-sync.md | 2026-09-16 | 2026-09-16: Sreekumar added new review points (root cause, resolution, attachment capture, status dropdown) that must be incorporated before this task is complete; due date extended to today. | planned
2026-09-16-intelligent-tracker-02 | 2026-09-16 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Ashwini | Review how developers close issues in Zoho (root cause, resolution, attachments) and identify fields to replicate in the Issues module UI. | 2026-09-16 | P1 | open |  | Ashwini, how a developer is closing a task? Just look at that once again in Zoho. | 2026-09-16-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-16-intelligent-tracker-03 | 2026-09-16 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Johan | Add the currency selector column to the CR entry screen UI (currently only present in the impact analysis view). | 2026-09-16 | P1 | open |  | you'll be adding that column in that entry screen, CR entry screen. It is not there now. | 2026-09-16-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-16-intelligent-tracker-04 | 2026-09-16 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Laxmikant | Add phase-level delay visibility (green/red per stage, payment milestone impact) and a morning alert for predicted delays to the project screen. | 2026-09-16 | P1 | open |  | Every day morning they should know that what is a predicted problem that can happen in the future. | 2026-09-16-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-16-intelligent-tracker-05 | 2026-09-16 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Laxmikant | Add separate flags for CR effort-vs-estimate overrun and schedule slip in the time tracker. | 2026-09-16 | P1 | open |  | there will be definitely a flat. Yes, estimated hours versus total hours will be there, sir. | 2026-09-16-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-16-intelligent-tracker-06 | 2026-09-16 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Ashwini | Post today's review comments for Issues, CR and Plan Tree in the group chat so Sreekumar can give sign-off. | 2026-09-16 | P1 | open |  | make sure that we put those review comments in the group. Based on that, I will give you the sign off in the chat. | 2026-09-16-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-16-intelligent-tracker-07 | 2026-09-16 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Ayush | Review Laxmikant's updated solution design document and sign off if it is acceptable. | 2026-09-16 | P1 | open |  | He sent it to me. I'll review it and I'll sign off on that if it is okay. | 2026-09-16-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-15-intelligent-tracker-03 | 2026-09-15 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Ashwini | Show Sreekumar in the application how CR items and issues resolve into work-item tasks. |  | P1 | open |  | Yeah, that we will show you on the website. | 2026-09-15-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-11-intelligent-tracker-02 | 2026-09-11 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Johan | Log detailed CR module tasks for today in Zoho and send the task ID to Ashwini. | 2026-09-11 | P2 | open |  | they will be noting down their detailed task in Zoho and giving a Task ID to Ashwini | 2026-09-11-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-11-intelligent-tracker-03 | 2026-09-11 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Samuel | Log detailed Issues module tasks for today in Zoho and send the task ID to Ashwini. | 2026-09-11 | P2 | open |  | they will be noting down their detailed task in Zoho and giving a Task ID to Ashwini | 2026-09-11-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-11-intelligent-tracker-08 | 2026-09-11 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Ayush | Speak with Laxmikant to plan the development plan and model for the build. | 2026-09-11 | P2 | open |  | I will speak to Lakshmi, plan development plan with model that's it | 2026-09-11-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-16-intelligent-tracker-01 | 2026-09-16 | Activity Tracker internal sync-up | Intelligent Tracker | intelligent-tracker | Samuel | Discuss with Laxmikant the feasibility and structural changes needed for the new issue fields from Sreekumar's design before building them. | 2026-09-16 | P2 | open |  | I wanted Sam to talk to you regarding the feasibility of that. I know it will work, but what is the structure change? | 2026-09-16-activity-tracker-sync.md | 2026-09-16 |  | planned
2026-09-16-lsp-01 | 2026-09-16 | CR: Distributor Line-Item Visibility and Claim Status Sync | unassigned | lsp | Ayush | Review the new lsp_claim_line_items table and added claim-table columns against the no-further-master-data-changes position agreed with Adwaith. |  | P1 | done |  | Existing claim table: add lsp_fy, lsp_totalnrclaimwithsr, lsp_totalpoclaimwithsr, plus the status-sync fields | CR_DISTRIBUTOR_LINE_ITEM_VISIBILITY_Revised (1).docx | 2026-09-16 |  | planned | review | Ayush compares the new tables and columns against the sign-off position and flags any conflicts to Adwaith. | List of new columns/tables from this CR |  | half-day | No further master data or DB column changes after sign-off (told to Adwaith on 2026-09-16). | 2026-09-16
2026-09-16-lsp-02 | 2026-09-16 | CR: Distributor Line-Item Visibility and Claim Status Sync | unassigned | lsp | Adwaith | Populate lsp_distributoremail for every distributor before the claim-status notification feature rolls out. |  | P2 | done |  | lsp_distributoremail is not populated for every distributor. Populate it before rollout or the notification silently sends to nobody. | CR_DISTRIBUTOR_LINE_ITEM_VISIBILITY_Revised (1).docx | 2026-09-16 |  | planned | other | Adwaith supplies the missing distributor email addresses for all distributor master records. |  |  | unknown | CR section 7.4 Notifications | 2026-09-16
2026-09-16-lsp-03 | 2026-09-16 | CR: Distributor Line-Item Visibility and Claim Status Sync | unassigned | lsp | Ayush | Agree and document a retention or archival policy for closed periodic closure line-item data. |  | P3 | done |  | Agree a retention or archival policy for closed periodic closures. | CR_DISTRIBUTOR_LINE_ITEM_VISIBILITY_Revised (1).docx | 2026-09-16 |  | planned | decide | Ayush proposes a retention window and confirms it with the DMS side. |  |  | unknown | CR section 8.6 Sizing | 2026-09-16